## Slide 1
GO-TO-MARKET · AUG 2026
Permissionless Campaigns
2-week launch campaign · 4 activation pillars · every piece already written
“No sales call. No agency. No permission.”
Launch campaign plan · full copy & scripts: Master Doc

## Slide 2
WHY WE RUN THIS CAMPAIGN
Three objectives, one launch
MASTER DOC ▸
CLOSE COMMUNITIES & PROJECTS
Convert the launch into signed demand.
First Verified cohort filled ($1,500 × N — the revenue line)
Flagship communities operating inside Rally (co-created campaign)
Project pipeline worked 1:1 with one-pager + case study
KPI: Verified calls booked · cohort filled · communities claimed
ACQUISITION NARRATIVE
Own one story: marketing without gatekeepers.
The Demo Video as acquisition engine — promoted at full throttle
KOLs launching real RLP-funded campaigns: the promotion IS the product
Every piece repeats the same hook, twice a week, for two weeks
KPI: video reach · new sign-ups · campaigns created
UNIFY THE CONCEPTS
One frame that connects everything Rally has built.
RLPs = working capital · Communities = distribution · Campaigns = the market
Network (open floor) vs Verified (main stage) — one clean mental model
Ends at the vision: “Rally, the Hub of Communities”
KPI: RLPs deployed into pools · consistent narrative across ~25 pieces
The campaign is designed so each pillar serves at least one objective — nothing publishes without a job.

## Slide 3
THE STRATEGY
Four activation pillars — everything else supports these
MASTER DOC ▸
1 · THE PERMISSIONLESS VIDEO
Master Doc §5, 11.5 ▸
The hero. Everything derives from it.
Demo Video promoted at full throttle from Day 1
KOLs launch real permissionless campaigns funded in RLPs
Teaser · countdown · cutdowns · receipts thread keep it alive
2 · SALES NARRATIVE & CO-MARKETING
Master Doc §6–7, 11 ▸
Attract communities and projects.
Verified & Network pitches + use-case articles
Call for Projects (first cohort) + flagship co-created campaign
Case study with real ROI → pipeline + “Hub of Communities” vision
3 · CREATORS CREATING CAMPAIGNS
Master Doc §9, 11 ▸
Social proof from other voices.
Creators launch campaigns with their RLPs — and tell it on video
Weekly Spotlight of the best community campaigns
Campaign Idea Battle: winning community idea gets funded
4 · CONCEPT EDUCATION
Master Doc §8, 10, 13 ▸
Lower the barrier to the first campaign.
“How It Works” · “Why RLPs Matter” · brief-writing guide
Live demo: a campaign launched in 10 minutes, on stream
X Space debrief + AMAs — objections answered in public

## Slide 4
PILLAR 1
The Permissionless Video
Serves: acquisition narrative + concept unification
One heavy production, ~25 pieces living off it — maximum leverage per euro
KOLs don't do ad reads: they launch real campaigns funded in RLPs. Their audience watches the product work
The hook carries the whole story: “Every campaign you've seen here was ours. That ends today.”
CONTENTS & TIMING
MASTER DOC ▸
THU 13
Teaser 15s — “Something permissionless is coming”
FRI 14
Countdown post — launch date reveal
MON 17
DEMO VIDEO (100s, script locked) + launch thread pinned + mailing
MON 17→
KOL activation: real RLP-funded campaigns + coordinated QT push
W1–W2
Cutdowns 15s / 30s — fresh angles keep it circulating
FRI 28
“Anatomy of a Campaign” receipts thread — the video, proven with screenshots
Master Doc §4–5, 11.5 ▸

## Slide 5
PILLAR 2
Sales Narrative & Co-marketing
Serves: close communities & projects (the revenue line)
Two clean offers: Network (open floor, free) vs Verified (main stage, $1,500)
Co-marketing built in: projects launch WITH us — Call for Projects, flagship co-created campaign
Everything doubles as sales material: one-pager, comparison visual, use cases, case study
CONTENTS & TIMING
MASTER DOC ▸
TUE 18
Verified thread + “Why Verified — 5 Use Cases” + one-pager → pipeline
WED 19
Network thread + Verified vs Network visual + CALL FOR PROJECTS (first cohort)
FRI 21
Flagship co-created campaign goes live (partner community)
W1–W2
1:1 outreach to Sept–Oct launches — the video is the pitch
WED 26
Case study “10 days after the video” + sales article → pipeline
THU 27
Vision: “Rally, the Hub of Communities” — the story that closes communities
Master Doc §6–7, 11.3–11.4 ▸

## Slide 6
PILLAR 3
Creators Creating Campaigns
Serves: acquisition narrative + social proof
The claim only lands when someone who isn't us says it
Creators spend their own RLPs on their own campaigns — the loop, demonstrated
Community content compounds: every spotlight makes the next creator want in
CONTENTS & TIMING
MASTER DOC ▸
FRI 21
Creator video #1 — “I launched a campaign, here's what happened” (their words)
MON 24
Spotlight thread: best community campaigns (recurring every Monday)
TUE 25
Partner video #2 — community-lead POV
W2
Poll feeds the Battle: “What would you launch a campaign for?”
SAT 29
Campaign Idea Battle — the winning community idea gets funded for real
Master Doc §9, 11.1–11.2, 11.6 ▸

## Slide 7
PILLAR 4
Concept Education
Serves: concept unification + lowering the barrier to campaign #1
Ten minutes from idea to live — but only if people know how
Education content is evergreen: it keeps converting after the campaign ends
Objections answered in public build trust faster than any ad
CONTENTS & TIMING
MASTER DOC ▸
MON 17
Article: “Permissionless Campaigns — How It Works” (evergreen explainer)
WED 19
Article: “Why RLPs Matter” — points become working capital
THU 20
Live demo: “Launch a campaign in 10 minutes” + guide “How to Write a Campaign Brief”
SAT 22
X Space: Creators & Partners AMA — first campaigns debrief
ALWAYS
Objections cheat sheet + tagline bank (Spaces, AMAs, replies)
Master Doc §5.4, 7.5, 8, 10, 13 ▸

## Slide 8
THE CALENDAR
12 days · color-coded by pillar
MASTER DOC ▸
Video
Sales
Creators
Education
PRE-LAUNCH: Thu 13 teaser · Fri 14 countdown
WEEK 1 · LAUNCH
MON 17
THE DROP
Demo Video + thread + mailing + KOL campaigns + How-It-Works
TUE 18
Verified
thread $1,500 + use cases + one-pager → pipeline
WED 19
Network
thread + comparison visual + Call for Projects + RLPs article
THU 20
Live Demo
“10 minutes” live build + brief guide
FRI 21
Creator Video #1
testimonial + flagship co-created campaign live
SAT 22
Debrief
X Space: creators & partners AMA
WEEK 2 · SOCIAL PROOF
MON 24
Spotlight
best community campaigns (every Monday)
TUE 25
Partner Video #2
community-lead testimonial
WED 26
Case Study
“10 days after” + sales article → pipeline + KOL push
THU 27
Vision
“Rally, the Hub of Communities”
FRI 28
Anatomy
receipts thread (screenshots) + cutdown
SAT 29
Community Day
AMA + Campaign Idea Battle (winner funded)

## Slide 9
THE ASK
What I need from design — all copy is final, design never waits for text
MASTER DOC ▸
WAVE 1 · BEFORE THE DROP
due Aug 12–14
Demo Video edit (script locked) — the only heavy lift
Teaser 15s + countdown graphic
QT kit for communities, creators & KOLs
OG images (thread + article) + email header
WAVE 2 · LAUNCH WEEK
due Aug 17–21
Verified one-pager PDF (the sales asset)
Verified vs Network comparison visual
Call for Projects banner + form header
2 X Space covers · 2 cutdowns · video lower-thirds
WAVE 3 · SOCIAL PROOF
due Aug 24–26
Spotlight template (reusable every Monday)
Big-number stat template (case study + numbers posts)
AMA cover + Idea Battle bracket
15 assets · 3 waves · full spec table with per-asset deadlines in the Master Doc §12 ▸

## Slide 10
DESIGN KIT · ALREADY PRODUCED
Pre-launch & launch day — ready to post
MASTER DOC ▸
TEASER · THU 13
COUNTDOWN 3·2·1 · FRI 14 →
LAUNCH THREAD OG · MON 17
“HOW IT WORKS” ARTICLE OG · MON 17
LIVE POST · MON 17
EMAIL HEADER · MON 17

## Slide 11
DESIGN KIT · ALREADY PRODUCED
Sales, Spaces & weekly templates
MASTER DOC ▸
VERIFIED ONE-PAGER · TUE 18
CALL FOR PROJECTS · WED 19
SPACE LIVE DEMO · THU 20
CREATORS & PARTNERS AMA · SAT 22
SPOTLIGHT TEMPLATE · EVERY MON
CASE STUDY “RECEIPTS” · WED 26
NETWORK VS VERIFIED · WED 19
IDEA BATTLE · SAT 29
WHY PERMISSIONLESS · W1
STILL WITH DESIGN/EDITOR
Demo Video edit · cutdowns 15/30s · KOL clips · lower-thirds
17 static assets produced in Rally's graphic line — regenerable in minutes (copy, dates, sizes).

## Slide 12
“The campaign button belongs
to everyone now.”
4 pillars · 3 objectives · 12 days · everything written.
Greenlight this week = we ship Monday Aug 17.
Master Doc — plan, copy, scripts, design ▸